## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Understand the problem statement and learn how AI can analyze contracts for GDPR/HIPAA compliance. | MUST HAVE | NO dependency | Manasa | 3- Completed
S1 | S1 | US-001 | Collect sample contracts and gather GDPR + HIPAA official documents for compliance reference. | MUST HAVE | Online docs | Manasa | 3- Completed
S1 | S1 | US-001 | Prepare the project structure: repo setup, virtual environment, dependencies, and SpaCy model installation. | MUST HAVE | Github repo | Manasa | 3- Completed
S1 | S1 | US-001 | Design initial workflow:Upload → Extract → Analyze → Score → Rewrite → Alert. | MUST HAVE | workflow tools | Manasa | 3- Completed
S1 | S1 | US-001 | Build basic Streamlit UI for uploading contracts and selecting GDPR/HIPAA frameworks. | MUST HAVE | streamlit | Manasa | 3- Completed
S1 | S1 | US-001 | Develop document ingestion and preprocessing module (PDF, DOCX, TXT). | MUST HAVE | PyPDF,doc2txt | Manasa | 3- Completed
S1 | S1 | US-001 | Implement backend risk analysis engine using Groq LLM to check compliance against GDPR/HIPAA rules. | MUST HAVE | Groq API | Manasa | 3- Completed
S2 | S2 | US-001 | Identify missing or incomplete clauses based on GDPR/HIPAA requirement mapping. | MUST HAVE | Risk Engine | Manasa | 3- Completed
S2 | S2 | US-001 | Implement AI-powered rewriting system to automatically generate corrected/complete clauses. | MUST HAVE | Groq LLM | Manasa | 3- Completed
S2 | S2 | US-001 | Add UI section for displaying rewritten/upgraded contract sections clearly to the user. | SHOULD HAVE | stramlit | Manasa | 3- Completed
S2 | S2 | US-001 | Provide downloadable outputs (PDF, JSON, updated text file). | SHOULD HAVE | python export libs | Manasa | 3- Completed
S3 | S3 | US-001 | Implement notification alerts (Slack/Email) for high-risk contracts. | SHOULD HAVE | API Keys | Manasa | 3- Completed
S3 | S3 | US-001 | Integrate all modules: analysis + rewriting + alerts into one smooth workflow. | MUST HAVE | All modules | Manasa | 3- Completed
S3 | S3 | US-001 | Conduct testing on complete system including edge cases and real-world contracts. | MUST HAVE | pytest | Manasa | 3- Completed
S3 | S3 | US-001 | Deploy to Render/PythonAnywhere and prepare final documentation. | MUST HAVE | Deployment | Manasa | 2- In Progress
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 75 | 37 | 27 | 26 | 22 | 19 | 12 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US ID | Task ID | Task Description | Task Start Date | Completion Date | Team Member | Activity | Status | Est. Hours | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14
US-001 | 1 | Understanding GDPR & HIPAA requirements + problem statement | 2025-10-01 | 2025-10-03 | Manasa | Research | 3 – Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Collect sample contracts + official compliance documents | 2025-10-02 | 2025-10-05 | Aditya | Research | 3 – Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 3 | Project repo setup, venv, requirements, SpaCy model setup | 2025-10-03 | 2025-10-06 | Jagadeesh | Build | 3 – Completed | 5 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 4 | Design the main workflow (Upload → Extract → Analyze → Score) | 2025-10-04 | 2025-10-08 | Manasa | Design | 3 – Completed | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 5 | Build basic Streamlit UI for contract upload + framework selection | 2025-10-08 | 2025-10-12 | Aditya | Coding | 3 – Completed | 10 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 6 | Implement document ingestion (PDF, DOCX, TXT) + preprocessing | 2025-10-10 | 2025-10-16 | Jagadeesh | Coding | 3 – Completed | 12 | 3 | 2 | 2 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 7 | Implement risk analysis engine using Groq LLM | 2025-10-12 | 2025-10-17 | Manasa | Coding | 3 – Completed | 14 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 8 | Identify missing GDPR/HIPAA clauses | 2025-10-18 | 2025-10-21 | Manasa | Analysis | 3-Completed | 6 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 9 | Build clause rewriting module | 2025-10-19 | 2025-10-26 | Jagadeesh | Coding | 3 – Completed | 14 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 10 | UI to display rewritten clauses | 2025-10-21 | 2025-10-28 | Aditya | Build | 3-Completed | 10 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 11 | Download outputs (PDF, JSON, TXT) | 2025-10-24 | 2025-10-30 | Manasa | Integration Test | 3 – Completed | 8 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 12 | Integrate rewriting + analysis modules | 2025-10-28 | 2025-11-04 | Entire Team | System Test | 3 – Completed | 12 | 3 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 13 | Implement Slack/Email notification alerts | 2025-11-05 | 2025-11-09 | Aditya | Coding | 3 – Completed | 10 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 14 | Full workflow integration (Analyze→Rewrite→Alert) | 2025-11-06 | 2025-11-11 | Manasa | Integration | 3 – Completed | 12 | 3 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 15 | Edge-case testing (real contracts) | 2025-11-07 | 2025-11-13 | Jagadeesh | System Test | 3 – Completed | 8 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 16 | Deployment (Render) + Documentation | 2025-11-09 | 2025-11-14 | Entire Team | Release | 2-In Progress | 10 | 3 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Difficulty understanding GDPR + HIPAA compliance requirements | Team conducted a detailed review of GDPR & HIPAA official documents
Sprint 1 | Day 4 | Issues extracting text from different file formats (PDF/DOCX) | Implemented pdfplumber + docx module and fixed extraction errors
Sprint 1 | Day 6 | Backend logic for risk analysis unclear | Brainstormed with team and finalized risk analysis rule-mapping structure
Sprint 2 | Day 2 | UI design flow for upload → analyze unclear | Conducted a whiteboard session to finalize UI + workflow mapping
Sprint 2 | Day 4 | Rewriting module outputs inconsistent | Tested multiple Groq prompts and refined rewriting instructions
Sprint 2 | Day 6 | Difficulty mapping missing clauses to GDPR/HIPAA rules | Created a structured "Clause Mapping Sheet" for reference
Sprint 2 | Day 8 | Confusion in returning rewritten text clearly to UI | Added separate Streamlit tabs for “Original”, “Risk”, and “Rewritten”
Sprint 3 | Day 3 | Notification alert system (Slack/Email) failing to trigger | Configured webhook + tested with sample alerts
Sprint 3 | Day 5 | Integration issues between analysis + rewriting | Conducted end-to-end integration test and debugged flow
Sprint 3 | Day 8 | Large contracts causing slow response time | Added text-chunking + streaming response
Sprint 3 | Day 11 | Deployment environment issues on Render | Reconfigured dependencies and fixed API environment variables
Sprint 3 | Day 14 | Final documentation missing clarity | Team collaboratively prepared clean and structured final documentation

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2024-10-01 | 2024-10-17 | Manasa, Aditya, Jagadeesh | Start analyzing GDPR & HIPAA rules in detail and mapping requirements | Stop assuming contract formats will be uniform | Continue researching compliance documents and improving understanding | Created a consolidated GDPR–HIPAA requirement sheet and finalized the workflow (Upload → Extract → Analyze → Score)
2 | Sprint 1 | 2024-10-01 | 2024-10-17 | Manasa | Start building stable preprocessing pipeline for PDFs/DOCX | Stop skipping edge-case testing in contract extraction | Continue validating extracted text quality | Implemented proper text extraction with preprocessing cleanup (whitespace removal, encoding fixes)
3 | Sprint 2 | 2024-10-18 | 2024-11-04 | Aditya | Start refining LLM prompts for accurate clause detection | Stop mixing risk-analysis tasks with rewriting tasks | Continue working on backend logic | Created optimized prompt templates and separated rewriting module into its own workflow
4 | Sprint 2 | 2024-10-18 | 2024-11-04 | Jagadeesh | Start developing rewriting module for missing clauses | Stop depending on raw outputs without post-processing | Continue improving Groq API integration | Implemented clause rewriting system and added cleaned, user-friendly rewritten output sections
5 | Sprint 3 | 2024-11-05 | 2024-11-14 | Manasa, Aditya, Jagadeesh | Start implementing notification alerts (Slack/Email) | Stop delaying integration testing until the end | Continue testing end-to-end workflows | Integrated alert module + performed full system testing and prepared deployment version